## Sheet1
7/1/2015	Design the common string algorithm
8/1/2015	Complete the design of common string algorithm and test it.
9/1/2015	Design the database structure, load some dummy data, connect it with algorithm, test it.
10/1/2015	Holiday - Saturday
11/1/2015	Holiday – Sunday
12/1/2015	Holiday – Public Holiday
13/1/2015	Complete remaining GUI, connect it with Algorithm and databaseStart creating interface
14/1/2015	Complete testing of System, BUG fixing.
15/1/2015	Create Presentation, Present it.